## Multi-Tech
State | Omega Effective Date | UBI Category | Tech Restricted | Multi-Tech Filing Date | Expected Multi-Tech Effective Date | Multi-Tech or Equivalent Filed and Approved | Multi-Tech Algorithm | Notes | VED Wave | VED Filing Date | VED Effective Date | 10% State | Sign Off Date | CWR Sign Off | Athena Systems Sign Off | Distribution Sign Off | SDA Wave | SDA Filing Date | SDA Effective Date | Sign Off Date | CWR Sign Off | Rainier Systems Sign Off | Distribution Sign Off | Tag PL Filing Date | Tag PL Effective Date | Sign Off Date | CWR Sign Off | Systems Sign Off | Distribution Sign Off | Tag Safeco Filing Date | Tag Safeco Effective Date | Sign Off Date | CWR Sign Off | Systems Sign Off | Distribution Sign Off | Highway Hero Filing Date | Highway Hero Date | CWR Sign Off | Systems/NB Sign Off | Distribution Sign Off | ByMile Filing Date | ByMile Effective Date | CWR Sign Off | Systems/NB Sign Off | Distribution Sign Off
AK | N/A | 5 | N | Not Included | Not included |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-11-22 | N/A
AL | 2017-02-18 | 4 | N | 2017-02-28 | 2017-04-17 | Yes | Moderate | SDA approved, VED language not. Still have broad rule, but not able to change enrollment discount. | 4 | 2017-02-16 | 2017-04-17 | N | 2017-03-15 | CRM | NRC |  | 4 | 2017-10-21 | 2017-04-17 | 2017-03-15 | CRM | DR
AR | 2017-05-22 | 1 | N | 2017-02-24 | 2017-05-22 | Yes | Algorithm not filed | Filed with Omega | 3 | N/A | 2017-03-20 | Y | 2017-02-15 | CRM | NRC | ER | 1 | N/A | 2016-05-13 | 2017-02-15 | CRM |  | ER
AZ | 2016-03-19 | 2 | N | 2017-06-01 | 2017-07-01 | Yes | Moderate | Broad language already in place | 3 | N/A | 2017-03-20 | N | 2017-02-15 | CRM | NRC | ER | 3 | 2016-09-11 | 2017-03-20 | 2017-02-15 | CRM | DR | ER
CA | N/A | 5 | Y | Not Included | Not included |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2017-02-21 | N/A
CO | 2016-08-20 | 1 | N | N/A | N/A | Yes | Algorithm not filed | Broad language and algorithm already in place | 2 | 2017-01-20 | 2017-02-20 | N | Past | CRM | NRC |  | 1 | 2017-02-16 | 2016-05-13 | Past | CRM
CT | 2017-06-17 | 2 | N | 2017-03-01 | 2017-07-17 | Yes | Algorithm not filed | Filed with Omega | 7 | 2017-09-07 | 2017-11-23 | Y | 2017-09-13 |  |  |  | 7 | TBD | 2017-11-20 | 2017-10-11
DC | 2017-10-14 | 3 | N | 2017-05-05 | 2017-10-14 | Filed | Moderate | Filed with Omega. Still being reviewed by the DOI. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2017-05-24 | N/A
DE | 2017-08-19 | 1 | N | 2017-06-01 | 2017-10-14 | Yes | Algorithm not filed | Broad language in place | 7 | 2017-09-05 | 2017-10-16 | N | 2017-09-13 |  |  |  | 1 | 2016-03-14 | 2016-05-13 | 2017-04-19
FL | 2017-10-14 | 4 | Y | 2017-06-07 | 2017-12-11 | No | Multi-Tech not yet filed | Plan to file with Omega. Dates tentative | 8 | 2017-08-10 | 2017-11-13 | N | 2017-10-18 |  |  |  | 7 | 2017-01-21 | 2017-11-20 | 2017-10-11
GA | 2017-04-15 | 1 | N | 2017-08-01 | 2017-11-13 | Yes | Algorithm not filed | Broad language already in place | 8 | 2017-08-10 | 2017-11-13 | Y | 2017-10-18 |  |  |  | 1 | 2017-02-18 | 2016-05-13 | 2017-10-11
HI | N/A | 5 | N/A | Not Included | Not included |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IA | 2017-10-14 | 4 | Y | 2017-05-24 | 2017-06-15 | No | Multi-Tech not yet filed | VED already filed. Potential to file with Omega. | 3 | 2017-02-18 | 2017-03-20 | Y | 2017-02-15 | CRM | NRC | ER | 3 | N/A | 2017-03-20 | 2017-02-15 | CRM | DR | ER
ID | 2017-04-15 | 2 | N | 2017-03-08 | 2017-04-15 | Yes | Algorithm not filed | Filed with Omega, as a filing amendment | 5 | 2017-04-22 | 2017-05-22 | Y | 2017-04-19 |  |  |  | 5 | 2016-04-13 | 2017-05-22 | 2017-04-19
IL | 2016-06-18 | 4 | Y | 2017-08-01 | 2017-09-18 | No | Algorithm not filed | VED/SDA already filed. DOI and DSO may be resistant to multi-tech language. | 2 | 2017-02-19 | 2017-02-20 | N | Past | CRM | NRC |  | 2 | 2017-04-22 | 2017-02-20 | Past | CRM
IN | 2017-04-15 | 3 | N | 2017-03-25 | 2017-04-17 | Yes | Algorithm not filed | Filed with Omega | 5 | 2017-02-18 | 2017-05-22 | Y | 2017-04-19 |  |  |  | 5 | 2016-04-13 | 2017-02-20 | 2017-04-19
KS | 2017-08-19 | 4 | N | 2017-04-14 | 2017-06-20 | Yes | Moderate | File with VED | 6 | 2017-04-20 | 2017-06-19 | N | 2017-05-17 |  |  |  | 6 | 2016-04-13 | 2017-06-19 | 2017-05-17
KY | 2016-03-19 | 1 | N | N/A | N/A | Yes | Algorithm not filed | Broad language and algorithm already in place | 1 | 2016-10-11 | 2016-12-20 | N | Past | CRM | NRC |  | 1 | N/A | 2016-05-13 | Past | CRM
LA | 2017-08-19 | 3 | N | 2017-05-17 | 2017-08-19 | No | Multi-Tech not yet filed | Plan to file with Omega | 6 | 2017-03-21 | 2017-06-19 | Y | 2017-05-17 |  |  |  | 6 | 2017-02-18 | 2016-12-10 | 2017-05-17
MA | 2017-11-13 | 4 | Y | TBD | TBD | No | Multi-Tech not yet filed | Multi-tech, 10%, etc unable to be filed currently due to DOI objections. Place on hold and revist post-Omega launch. | 8 | 2017-04-24 | 2017-11-13 | Y | 2017-10-18 |  |  |  | N/A | 2016-04-13 | N/A | 2017-04-19
MD | 2017-06-17 | 3 | N | 2017-09-01 | 2017-10-16 | No | Multi-Tech not yet filed | Unable to file with Omega. File with VED. MD is File and Use. | 7 | 2017-07-09 | 2017-10-16 | N | 2017-09-13 |  |  |  | 5 | 2017-03-23 | 2017-11-20 | 2017-04-19
ME | 2016-06-18 | 1 | N | 2017-04-20 | 2017-06-17 | Yes | Algorithm not filed | Broad language in place. | 6 | 2017-04-13 | 2017-06-20 | Y | 2017-05-17 |  |  |  | 1 | 2016-04-12 | 2016-05-13 | 2017-05-17
MI | 2016-10-15 | 2 | N | 2017-06-01 | 2017-07-16 | Yes | Algorithm not filed | Broad language in place. | 2 | 2016-12-05 | 2017-02-20 | N | Past | CRM | NRC |  | 2 | 2017-02-19 | 2017-06-19 | Past | CRM
MN | 2016-10-15 | 1 | N | 2017-06-01 | 2017-07-16 | Yes | Algorithm not filed | Broad language in place. | 1 | 2016-11-10 | 2017-02-20 | N | Past | CRM | NRC |  | 1 | 2017-09-21 | 2016-05-13 | Past | CRM
MO | 2017-08-21 | 3 | N | 2017-06-26 | 2017-08-21 | Yes | Moderate | Plan to file with Omega | 8 | 2017-10-05 | 2017-11-13 | N | 2017-10-18 |  |  |  | 1 | N/A | 2016-05-13 | 2017-10-11
MS | 2017-10-14 | 2 | N | 2017-06-02 | 2017-07-02 | Yes | Algorithm not filed | Filed with Omega | 5 | 2017-03-23 | 2017-05-22 | Y | 2017-04-19 |  |  |  | 5 | N/A | 2017-05-22 | 2017-04-19
MT | N/A | 5 | N/A | Not Included | Not included |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | N/A
NC | 2017-10-14 | 5 | N/A | Not Included | Not included |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-04-13 | N/A
ND | 2017-08-19 | 5 | N/A | 2017-09-11 | 2017-12-11 | No | Multi-Tech not yet filed | File rule and algorithm for TBYB. No plans for RT yet. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-10-11 | N/A
NE | 2017-06-17 | 1 | N | 2017-05-31 | 2017-06-17 | Yes | Algorithm not filed | Broad language already in place | 3 | N/A | 2017-03-20 | Y | 2017-02-15 | CRM | NRC | ER | 1 | 2016-02-13 | 2016-05-13 | 2017-02-15 | CRM |  | ER
NH | 2016-08-20 | 2 | N | 2016-10-27 | 2017-01-23 | Yes | Algorithm not filed | Broad language filed with VED. | 2 | 2017-01-21 | 2017-02-20 | N | Past | CRM | NRC |  | 2 | 2017-01-21 | 2017-03-20 | Past | CRM
NJ | 2017-02-18 | 4 | Y | 2017-06-15 | 2017-09-18 | Filed | Moderate | Filed with Omega 1.1. Under review by the DOI. | 4 | 2017-03-18 | 2017-04-17 | Y | 2017-03-15 | CRM | NRC |  | 4 | 2016-03-14 | 2017-04-17 | 2017-03-15 | CRM | DR
NM | N/A | 2 | N | 2017-05-15 | 2017-07-16 | Yes | Algorithm not filed | VED/SDA already filed. Plan to file with Tag | 3 | N/A | 2017-03-20 | Y | 2017-02-15 | CRM | NRC | ER | N/A | 2016-04-13 | N/A | 2017-02-15 | CRM |  | ER
NV | 2017-06-17 | 4 | N | 2016-12-15 | 2017-11-13 | Filed | Moderate | Filed with Omega. Still being reviewed by the DOI. | 7 | 2017-09-09 | 2017-10-16 | N | 2017-09-13 |  |  |  | 6 | 2017-03-18 | 2017-03-20 | 2017-05-17
NY | 2017-06-17 | 4 | N | 2017-05-15 | 2017-09-18 | No | Multi-Tech not yet filed | Attempt to file with Tag. May require separate filings. | 4 | 2017-01-17 | 2017-04-20 | Y | 2017-03-15 | CRM | NRC |  | TBD | 2016-10-11 | TBD | 2017-03-15 | CRM (10% is signed off, SDA is not)
OH | 2016-10-15 | 2 | N | 2017-06-01 | 2017-07-16 | No | Algorithm not filed | Broad rule in place. | Pilot | 2016-03-21 | 2016-04-20 | Y | Past | N/A | N/A | N/A | 2 | 2017-05-20 | 2017-02-20 | Past | CRM
OK | 2016-08-20 | 4 | Y | 2017-05-04 | 2017-07-16 | Yes | Algorithm not filed | Broad language already in place | 4 | N/A | 2017-04-20 | N | 2017-03-15 | CRM | NRC |  | 4 | 2016-12-05 | 2017-04-17 | 2017-03-15 | CRM | DR
OR | 2016-08-20 | 2 | N | 2016-07-20 | 2016-08-20 | Yes | Broad | Broad language and algorithm already in place | 2 | N/A | 2017-02-20 | N | Past | CRM | NRC |  | 2 | 2016-03-14 | 2017-04-17 | Past | CRM
PA | 2017-08-20 | 3 | N | 2017-07-20 | 2017-11-13 | No | Multi-Tech not yet filed | Omega already filed, file with VED/SDA | 8 | 2017-09-13 | 2017-11-13 | N | 2017-10-18 |  |  |  | 5 | N/A | 2017-02-20 | 2017-04-19
RI | 2017-10-14 | 4 | N | 2017-04-22 | 2017-11-13 | No | Multi-Tech not approved. | 10%, SDA approved. Multi-tech not approved. | 5 | 2017-04-22 | 2017-05-22 | Y | 2017-04-19 |  |  |  | 5 | N/A | 2017-05-22 | 2017-04-19
SC | 2017-08-19 | 4 | N | 2017-02-24 | 2017-08-21 | Yes | Moderate | Filed with Omega. Have to notify DOI of changes to factors or the reiew period. | 8 | 2017-05-24 | 2017-11-13 | Y | 2017-10-18 |  |  |  | 7 | 2017-03-18 | 2017-11-20
SD | N/A | 5 | N/A | Not Included | Not included |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2017-07-23 | N/A
TN | 2017-04-17 | 1 | N | 2016-09-01 | 2016-10-26 | Yes | Algorithm not filed | Broad language and algorithm already in place | 2 | N/A | 2017-02-20 | N | Past | CRM | NRC |  | 1 | 2017-08-22 | 2016-05-13 | Past | CRM
TX | 2016-08-20 | 3 | N | 2017-05-15 | 2017-09-18 | No | Moderate | File with Tag, SDA | 3 | 2016-12-29 | 2017-03-20 | N | 2017-02-15 | CRM | NRC | ER | TBD | N/A | TBD | 2017-02-15 | CRM | DR | ER
UT | 2016-06-18 | 1 | N | 2016-11-01 | 2016-12-10 | Yes | Algorithm not filed | Broad language already in place | 1 | 2016-11-10 | 2016-12-20 | N | Past | CRM | NRC |  | 1 | 2016-03-29 | 2016-05-13 | Past | CRM
VA | 2017-08-19 | 3 | N | 2017-06-21 | 2017-08-21 | Filed | Algorithm not filed | Filed with Omega | 6 | 2017-04-20 | 2017-06-19 | Y | 2017-05-17 |  |  |  | 6 | N/A | 2016-12-10 | 2017-05-17
VT | 2017-04-15 | 1 | N | 2017-03-09 | 2017-05-22 | Filed | Algorithm not filed | Filed with Omega. Still being reviewed by the DOI. | 6 | 2017-04-13 | 2017-06-19 | N | 2017-05-17 |  |  |  | 1 | N/A | 2016-05-13 | 2017-05-17
WA | TBD | 4 | Y | 2017-05-24 | 2017-11-13 | No | Multi-Tech not yet filed | Filing with Omega. RT is new to WA PL. | 8 | 2017-09-15 | 2017-11-13 | N | 2017-10-18 |  |  |  | 7 | 2016-12-29 | 2017-11-20 | 2017-10-11
WI | 2016-03-19 | 1 | N | 2016-11-01 | 2016-12-10 | Yes | Algorithm not filed | Broad language filed with VED. Algorithm not filed | 1 | 2016-11-10 | 2016-12-20 | N | Past | CRM | NRC |  | 1 | N/A | 2016-05-13 | Past | CRM
WV | 2017-06-17 | 2 | N | 2017-02-28 | 2017-05-22 | Yes | Algorithm not filed | Filed with Omega | 7 | 2017-07-16 | 2017-10-16 | N | 2017-09-13 |  |  |  | 6 | 2017-01-19 | 2016-12-10 | 2017-05-17
WY | 2017-06-17 | 5 | N/A | Not Included | Not included |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2016-04-13 | N/A

## VED
State | VED Wave | VED Filing Date | VED Effective Date | State Uses 10 Percent | VED to 10 Percent Transition | Sign Off Date | CWR Sign Off | Athena Systems Sign Off | Distribution Sign Off
KY | 1 | 2016-10-11 | 2016-12-20 | N | 2017-07-17 | Past | CRM | NRC
MN | 1 | 2016-11-10 | 2017-02-20 | N | 2017-08-21 | Past | CRM | NRC |  | Color Code
UT | 1 | 2016-11-10 | 2016-12-20 | N | 2017-07-17 | Past | CRM | NRC |  | Filed
WI | 1 | 2016-11-10 | 2016-12-20 | N | 2017-07-17 | Past | CRM | NRC |  | Past Filing Date
CO | 2 | 2017-01-20 | 2017-02-20 | N | 2017-07-17 | Past | CRM | NRC
IL | 2 | 2016-12-05 | 2017-02-20 | N | 2017-09-18 | Past | CRM | NRC
MI | 2 | 2017-01-21 | 2017-02-20 | N | 2017-07-17 | Past | CRM | NRC
NH | 2 | N/A | 2017-02-20 | N | 2017-07-17 | Past | CRM | NRC
OR | 2 | N/A | 2017-02-20 | N | 2017-09-18 | Past | CRM | NRC
TN | 2 | 2017-02-19 | 2017-02-20 | N | 2017-08-21 | Past | CRM | NRC
AR | 3 | N/A | 2017-03-20 | Y | Not Required | 2017-02-15 | CRM | NRC | ER
AZ | 3 | 2017-02-18 | 2017-03-20 | N | 2017-08-21 | 2017-02-15 | CRM | NRC | ER
IA | 3 | N/A | 2017-03-20 | Y | Not Required | 2017-02-15 | CRM | NRC | ER
NE | 3 | N/A | 2017-03-20 | Y | Not Required | 2017-02-15 | CRM | NRC | ER
NM | 3 | N/A | 2017-03-20 | Y | Not Required | 2017-02-15 | CRM | NRC | ER
TX | 3 | 2016-12-29 | 2017-03-20 | N | 2017-12-18 | 2017-02-15 | CRM | NRC | ER
NJ | 4 | 2017-03-18 | 2017-04-17 | Y | Not Required | 2017-03-15 | CRM | NRC | ER
NY | 4 | N/A | 2017-04-17 | Y | Not Required | 2017-03-15 | CRM | NRC | ER
OK | 4 | 2017-01-17 | 2017-04-17 | N | 2017-08-21 | 2017-03-15 | CRM | NRC | ER
ID | 5 | 2017-04-22 | 2017-05-22 | Y | Not Required | 2017-04-19 | CRM | NRC | ER
IN | 5 | 2017-02-18 | 2017-05-22 | Y | Not Required | 2017-04-19 | CRM | NRC | ER
MS | 6 | 2017-04-20 | 2017-06-19 | Y | Not Required | 2017-05-17 | CRM | NRC
KS | 6 | 2017-04-13 | 2017-06-19 | Y | Not Required | 2017-05-17 | CRM | NRC
ME | 6 | 2017-04-20 | 2017-06-19 | Y | Not Required | 2017-05-17 | CRM | NRC
VT | 6 | 2017-03-21 | 2017-06-19 | Y | Not Required | 2017-05-17 | CRM | NRC
LA | 7 | 2017-04-20 | 2017-10-16 | Y | Not Required | 2017-05-17
VA | 7 | 2017-07-06 | 2017-10-16 | Y | Not Required | 2017-09-13
CT | 7 | 2017-07-16 | 2017-10-16 | Y | Not Required | 2017-09-13
MD | 7 | 2017-08-01 | 2017-10-16 | Y | Not Required | 2017-09-13
NV | 7 | 2017-07-09 | 2017-10-16 | Y | Not Required | 2017-09-13
WV | 7 | 2017-09-09 | 2017-10-16 | Y | Not Required | 2017-09-13
RI | 8 | 2017-05-30 | 2017-11-13 | Y | Not Required | 2017-10-18
DE | 8 | 2017-09-07 | 2017-11-13 | Y | Not Required | 2017-09-13
FL | 8 | 2017-10-05 | 2017-12-11 | Y | Not Required | 2017-10-18
GA | 8 | 2017-08-10 | 2017-11-13 | Y | Not Required | 2017-10-18
MA | 8 | 2017-09-15 | 2017-12-11 | Y | Not Required | 2017-10-18
MO | 8 | 2017-08-10 | 2017-11-13 | Y | Not Required | 2017-10-18
PA | 8 | 2017-07-20 | 2017-11-13 | Y | Not Required | 2017-10-18
SC | 8 | 2017-09-13 | 2017-11-13 | Y | Not Required | 2017-10-18
WA | 8 | 2017-07-01 | 2017-11-13 | Y | Not Required | 2017-10-18
AL | N/A | N/A | N/A | N/A | Not Required | N/A | CRM | NRC | ER
AK | N/A | N/A | N/A | N/A | Not Required | N/A | N/A | N/A | N/A
CA | N/A | N/A | N/A | N/A | Not Required | N/A | N/A | N/A | N/A
DC | N/A | N/A | N/A | N/A | Not Required | N/A | N/A | N/A | N/A
HI | N/A | N/A | N/A | N/A | Not Required | N/A | N/A | N/A | N/A
MT | N/A | N/A | N/A | N/A | Not Required | N/A | N/A | N/A | N/A
NC | N/A | N/A | N/A | N/A | Not Required | N/A | N/A | N/A | N/A
ND | N/A | N/A | N/A | N/A | Not Required | N/A | N/A | N/A | N/A
SD | N/A | N/A | N/A | N | Not Required | N/A | N/A | N/A | N/A
WY | N/A | N/A | N/A | N/A | Not Required | N/A | N/A | N/A | N/A
OH | Pilot | 2016-03-21 | 2016-04-20 | Y | Not Required | Y | N/A | N/A | N/A

## SDA
State | SDA Wave | SDA Filing Date | SDA Effective Date | Sign Off Date | CWR Sign Off | Rainier Systems Sign Off | Distribution Sign Off
AZ | 3 | 2017-02-18 | 2017-03-20 | 2017-02-15 | CRM | DR | ER
IA | 3 | 2017-02-18 | 2017-03-20 | 2017-02-15 | CRM | DR | ER
AL | 4 | 2017-02-16 | 2017-04-17 | 2017-03-15 | CRM | DR
NJ | 4 | 2017-03-18 | 2017-04-17 | 2017-03-15 | CRM | DR
OK | 4 | 2017-03-18 | 2017-04-17 | 2017-03-15 | CRM | DR
ID | 5 | 2017-04-22 | 2017-05-22 | 2017-04-19 | CRM
IN | 5 | 2017-04-22 | 2017-05-22 | 2017-04-19 | CRM
KS | 6 | 2017-05-20 | 2017-06-19 | 2017-05-17 | CRM
MS | 6 | 2017-04-20 | 2017-06-19 | 2017-05-17 | CRM
LA | 7 | 2017-03-21 | 2017-10-23 | 2017-09-13 | CRM
CT | 7 | 2017-07-01 | 2017-10-23 | 2017-09-13
MD | 7 | 2017-08-01 | 2017-10-23 | 2017-09-13
NV | 7 | 2017-07-01 | 2017-10-23 | 2017-09-13
WV | 7 | 2017-09-01 | 2017-10-23 | 2017-09-13
VA | 7 | 2017-06-17 | 2017-10-23 | 2017-09-13
FL | 9 | 2017-08-22 | 2017-12-11 | 2017-10-11
NY | 8 | 2017-05-20 | 2017-11-13 | 2017-10-11
PA | 8 | 2017-07-20 | 2017-11-13 | 2017-10-11
RI | 8 | 2017-04-22 | 2017-11-13 | 2017-10-11
SC | 8 | 2017-05-24 | 2017-11-13 | 2017-10-11
TX | 9 | 2017-09-01 | 2017-12-11 | 2017-10-11 |  | DR | ER
WA | 9 | 2017-08-23 | 2017-12-11 | 2017-10-11
AK | N/A | N/A | N/A | N/A
CA | N/A | N/A | N/A | N/A
DC | N/A | N/A | N/A | N/A
HI | N/A | N/A | N/A | N/A
MA | N/A | N/A | N/A | N/A
MT | N/A | N/A | N/A | N/A
NC | N/A | N/A | N/A | N/A
ND | N/A | N/A | N/A | N/A
NM | N/A | N/A | N/A | N/A |  |  | ER
SD | N/A | N/A | N/A | N/A
WY | N/A | N/A | N/A | N/A
AR | 1 | 2016-03-14 | 2016-05-13 | Past
CO | 1 | 2016-04-12 | 2016-05-13 | Past
DE | 1 | 2016-02-13 | 2016-05-13 | Past
GA | 1 | 2016-03-29 | 2016-05-13 | Past
KY | 1 | 2016-03-14 | 2016-05-13 | Past
ME | 1 | 2016-03-14 | 2016-05-13 | Past
MN | 1 | 2016-04-13 | 2016-05-13 | Past
MO | 1 | 2016-04-13 | 2016-05-13 | Past
NE | 1 | 2016-04-13 | 2016-05-13 | Past
OH | 1 | 2017-01-21 | 2016-05-13 | Past
TN | 1 | 2016-04-13 | 2016-05-13 | Past
UT | 1 | 2016-04-13 | 2016-05-13 | Past
VT | 1 | 2016-04-13 | 2016-05-13 | Past
WI | 1 | 2016-04-13 | 2016-05-13 | Past
IL | 2 | 2017-02-19 | 2017-02-20 | Past | CRM
MI | 2 | 2016-12-05 | 2017-02-20 | Past | CRM
NH | 2 | 2017-01-21 | 2017-02-20 | Past | CRM
OR | 2 | 2016-12-29 | 2017-02-20 | Past | CRM

## Tag
State | Tag PL Wave | Tag PL Filing Date | Tag PL Effective Date | Sign Off Date | CWR Sign Off | Systems Sign Off | Distribution Sign Off | Tag Safeco Wave | Tag Safeco Filing Date | Tag Safeco Effective Date | Sign Off Date | CWR Sign Off | Systems Sign Off | Distribution Sign Off | Highway Hero Filing Date | Highway Hero Date | CWR Sign Off | Systems/NB Sign Off | Distribution Sign Off
CO | 1 | Not required | 2017-03-20 | 2017-02-18 | CRM |  |  | 5 | 2018-04-21 | 2018-05-21 | 2018-04-20 | CRM
KY | 1 | Not required | 2017-03-20 | 2017-02-18 | CRM |  |  | 2 | 2018-09-14 | 2018-11-13 | 2018-10-13
TN | 1 | Not required | 2017-03-20 | 2017-02-18 | CRM |  |  | 3 | 2017-12-23 | 2018-01-22 | 2017-12-22
WI | 1 | Not required | 2017-03-20 | 2017-02-18 | CRM |  |  | 1 | 2017-08-19 | 2017-09-18 | 2017-08-18 | CRM
AL | 2 | Not required | 2017-07-26 | 2017-06-26 | CRM |  |  | 3 | 2017-12-23 | 2018-01-22 | 2017-12-22
ID | 2 | Not required | 2017-07-26 | 2017-06-26 | CRM |  |  | N/A | Not included | Not included | Not included
MN | 2 | Not required | 2017-07-26 | 2017-06-26 | CRM |  |  | 2 | 2017-10-14 | 2017-11-13 | 2017-10-13
PA | 2 | Not required for Tag | 2017-07-26 | 2017-06-26 | CRM |  |  | 2 | 2017-09-14 | 2017-11-13 | 2017-10-13
UT | 2 | Not required | 2017-07-26 | 2017-06-26 | CRM |  |  | 1 | 2017-08-19 | 2017-09-18 | 2017-08-18 | CRM
AR | 3 | Not required | 2017-08-21 | 2017-07-22 | CRM |  |  | 2 | 2017-09-14 | 2017-11-13 | 2017-10-13
IN | 3 | Not required | 2017-08-21 | 2017-07-22 | CRM |  |  | 5 | 2018-04-21 | 2018-05-21 | 2018-04-20
ME | 3 | Not required | 2017-08-21 | 2017-07-22 | CRM |  |  | TBD | Not required | TBD | #VALUE! | CRM
MI | 3 | Not required | 2017-08-21 | 2017-07-22 | CRM |  |  | 1 | 2017-08-19 | 2017-09-18 | 2017-08-18
OH | 3 | 2017-06-01 | 2017-08-21 | 2017-07-22 | CRM |  |  | 3 | 2017-12-23 | 2018-01-22 | 2017-12-22
AZ | 4 | Not required | 2017-09-18 | 2017-08-19 |  |  |  | 3 | 2017-12-23 | 2018-01-22 | 2017-12-22
CT | 4 | Not required | 2017-09-18 | 2017-08-19 |  |  |  | 2 | 2017-09-14 | 2017-11-13 | 2017-10-13
LA | 4 | 2017-05-17 | 2017-09-18 | 2017-08-19 |  |  |  | 4 | 2018-01-18 | 2018-03-19 | 2018-02-16
MA | 4 | TBD | 2017-09-18 | 2017-08-19 |  |  |  | 4 | 2017-09-20 | 2018-03-19 | 2018-02-16
MS | 4 | Not required | 2017-09-18 | 2017-08-19 |  |  |  | 2 | 2017-10-14 | 2017-11-13 | 2017-10-13
OK | 4 | Not required | 2017-09-18 | 2017-08-19 |  |  |  | 5 | 2018-03-22 | 2018-05-21 | 2018-04-20
OR | 4 | Not required | 2017-09-18 | 2017-08-19 |  |  |  | 3 | 2017-12-23 | 2018-01-22 | 2017-12-22
WV | 4 | Not required | 2017-09-18 | 2017-08-19 |  |  |  | 2 | 2017-09-14 | 2017-11-13 | 2017-10-13
GA | 5 | Not required | 2017-11-13 | 2017-10-14 |  |  |  | 1 | 2017-07-20 | 2017-09-18 | 2017-08-18 | CRM
FL | 5 | 2017-07-10 | 2017-11-13 | 2017-10-14 |  |  |  | 4 | 2017-12-19 | 2018-03-19 | 2018-02-16
IL | 5 | 2017-07-10 | 2017-11-13 | 2017-10-14 |  |  |  | 4 | 2018-02-17 | 2018-03-19 | 2018-02-16
MD | 5 | 2017-08-01 | 2017-11-13 | 2017-10-14 |  |  |  | 4 | 2018-01-18 | 2018-03-19 | 2018-02-16
MO | 5 | 2017-07-10 | 2017-11-13 | 2017-10-14 |  |  |  | 3 | 2017-12-23 | 2018-01-22 | 2017-12-22
NH | 5 | Not required | 2017-11-13 | 2017-10-14 |  |  |  | 4 | 2018-02-17 | 2018-03-19 | 2018-02-16
NJ | 5 | 2017-07-10 | 2017-11-13 | 2017-10-14 |  |  |  | N/A | Not included | Not included | Not included
NM | 5 | Not required | 2017-11-13 | 2017-10-14 |  |  |  | 1 | 2017-08-19 | 2017-09-18 | 2017-08-18 | CRM
NV | 5 | Not required | 2017-11-13 | 2017-10-14 |  |  |  | 5 | 2018-03-22 | 2018-05-21 | 2018-04-20
NY | 5 | 2017-07-06 | 2017-11-13 | 2017-10-14 |  |  |  | 3 | 2017-10-24 | 2018-01-22 | 2017-12-22
VA | 5 | 2017-07-10 | 2017-11-13 | 2017-10-14 |  |  |  | 4 | 2018-01-18 | 2018-03-19 | 2018-02-16
WA | 5 | 2017-07-17 | 2017-12-11 | 2017-11-11 |  |  |  | 3 | 2017-09-24 | 2018-01-22 | 2017-12-22
TX | 5.5 | 2017-08-01 | 2017-12-11 | 2017-11-11 |  |  |  | 3 | 2017-11-23 | 2018-01-22 | 2017-12-22
DC | 6 | Not required | 2018-01-22 | 2017-12-23 |  |  |  | N/A | Not included | Not included | Not included
DE | 6 | 2017-07-10 | 2018-01-22 | 2017-12-23 |  |  |  | TBD | #VALUE! | TBD | #VALUE!
IA | 6 | 2017-07-10 | 2018-01-22 | 2017-12-23 |  |  |  | 4 | 2018-02-02 | 2018-03-19 | 2018-02-16
KS | 6 | Not required | 2018-01-22 | 2017-12-23 |  |  |  | 4 | 2018-02-17 | 2018-03-19 | 2018-02-16
NE | 6 | Not required | 2018-01-22 | 2017-12-23 |  |  |  | 2 | 2018-10-14 | 2018-11-13 | 2018-10-13
RI | 6 | 2017-06-19 | 2018-01-22 | 2017-12-23 |  |  |  | N/A | Not included | Not included | Not included
SC | 6 | Not required | 2018-01-22 | 2017-12-23 |  |  |  | 3 | 2017-06-17 | 2018-01-22 | 2017-12-22
VT | 6 | Not required | 2018-01-22 | 2017-12-23 |  |  |  | 5 | 2018-04-21 | 2018-05-21 | 2018-04-20
AK | N/A | Not Included | Not Included | Not Included |  |  |  | N/A | Not included | Not included | Not included
CA | N/A | Not Included | Not Included | Not included |  |  |  | N/A | Not included | Not included | Not included
HI | N/A | Not Included | Not Included | Not included |  |  |  | N/A | Not included | Not included | Not included
MT | N/A | Not Included | Not Included | Not included |  |  |  | 5 | 2018-04-21 | 2018-05-21 | 2018-04-20
NC | N/A | Not Included | Not Included | Not included |  |  |  | N/A | Not included | Not included | Not included
ND | N/A | 2017-09-11 | 2017-09-11 | Not included |  |  |  | 5 | 2018-03-22 | 2018-05-21 | 2018-04-20
SD | N/A | Not Included | Not Included | Not included |  |  |  | 4 | 2018-02-17 | 2018-03-19 | 2018-02-16
WY | N/A | Not Included | Not Included | Not included |  |  |  | 2 | 2017-10-14 | 2017-11-13 | 2017-10-13
Formulas:
Sign Off Date = [Tag PL Effective Date]-30
Sign Off Date = [Tag Safeco Effective Date]-31
Tag Safeco Filing Date = [Tag Safeco Effective Date]-30
Tag PL Filing Date = VLOOKUP([State],'Multi-Tech'!$A2:I52,5,FALSE)
Tag PL Effective Date = VLOOKUP([State],'Multi-Tech'!$A2:I52,5,FALSE)

## ByMile
State | ByMile Filing Date | ByMile Effective Date | Sign Off Date | CWR Sign Off | Systems/NB Sign Off | Distribution Sign Off
AK
AL
AR
AZ
CA
CO
CT
DC
DE
FL
GA
HI
IA
ID
IL
IN
KS
KY
LA
MA
MD
ME
MI
MN
MO
MS
MT
NC
ND
NE
NH
NJ
NM
NV
NY
OH
OK
OR
PA
RI
SC
SD
TN
TX
UT
VA
VT
WA
WI
WV
WY

## TBYB
State | TBYB Wave | TBYB Filing Date | Multi Tech Effective Date | TBYB Effective Date | Sign Off Date | CWR Sign Off | Systems/NB Sign Off | Distribution Sign Off
CO | 1 | N/A | N/A | Complete | N/A | CRM
KY | 1 | N/A | N/A | Complete | N/A | CRM
GA | 1 | 2017-08-01 | 2017-11-13 | Complete | 2017-10-14 | CRM
MO | 1 | 2017-06-26 | 2017-08-21 | Complete | 2017-07-22 | CRM
MN | 1 | 2017-06-01 | 2017-07-16 | Complete | 2017-06-16 | CRM
NM | 1 | 2017-05-15 | 2017-07-16 | Complete | 2017-06-16 | CRM
ME | 1 | 2017-04-20 | 2017-06-17 | Complete | 2017-05-18 | CRM
NE | 1 | 2017-05-31 | 2017-06-17 | Complete | 2017-05-18 | CRM
AR | 1 | 2017-02-24 | 2017-05-22 | Complete | 2017-04-22 | CRM
VT | 1 | 2017-03-09 | 2017-05-22 | Complete | 2017-04-22 | CRM
ID | 1 | 2017-03-08 | 2017-04-15 | Complete | 2017-03-16 | CRM
UT | 1 | 2016-11-01 | 2016-12-10 | Complete | 2016-11-10 | CRM
WI | 1 | 2016-11-01 | 2016-12-10 | Complete | 2016-11-10 | CRM
TN | 1 | 2016-09-01 | 2016-10-26 | Complete | 2016-09-26 | CRM
DE | 2 | 2017-06-01 | 2017-10-14 | Complete | 2017-09-14 | CRM
WV | 2 | 2017-02-28 | 2017-05-22 | Complete | 2017-04-22 | CRM
AL | 3 | 2017-02-28 | 2017-04-17 | Complete | 2017-03-18 | CRM
IN | 3 | 2017-03-25 | 2017-04-17 | Complete | 2017-03-18 | CRM
OR | 3 | 2016-07-20 | 2016-08-20 | Complete | 2016-07-21 | CRM
MI | 4 | 2017-06-01 | 2017-07-16 | Complete | 2017-06-16 | CRM
CT | 5 | 2017-03-01 | 2017-07-17 | 2017-07-17 | 2017-06-26 | CRM
OH | 5 | 2017-06-01 | 2017-07-16 | 2017-07-17 | 2017-06-26 | CRM
AZ | 5 | 2017-06-01 | 2017-07-01 | 2017-07-17 | 2017-06-26 | CRM
OK | 6 | 2017-05-04 | 2017-07-16 | 2017-08-21 | 2017-07-31
KS | 6 | 2017-04-14 | 2017-06-20 | 2017-08-21 | 2017-07-31
NH | 6 | 2016-10-27 | 2017-01-23 | 2017-08-21 | 2017-07-31
DC | 7 | 2017-05-05 | 2017-10-14 | 2017-09-18 | 2017-08-28
NJ | 7 | 2017-06-15 | 2017-09-18 | 2017-09-18 | 2017-08-28
SC | 7 | 2017-02-24 | 2017-08-21 | 2017-09-18 | 2017-08-28
VA | 7 | 2017-06-21 | 2017-08-21 | 2017-09-18 | 2017-08-28
LA | 7 | 2017-05-17 | 2017-08-19 | 2017-09-18 | 2017-08-28
IL | 8 | 2017-09-01 | 2017-10-16 | 2017-10-16 | 2017-09-25
NY | 8 | 2017-09-01 | 2017-10-16 | 2017-10-16 | 2017-09-25
MS | 8 | 2017-07-01 | 2017-10-16 | 2017-10-16 | 2017-09-25
NV | 9 | 2016-12-15 | 2017-11-13 | 2017-11-13 | 2017-10-23
PA | 9 | 2017-07-20 | 2017-11-13 | 2017-11-13 | 2017-10-23
RI | 9 | 2017-04-22 | 2017-11-13 | 2017-11-13 | 2017-10-23
MD | 9 | 2017-09-01 | 2017-10-16 | 2017-11-13 | 2017-10-23
IA | 9 | 2017-05-24 | 2017-06-15 | 2017-11-13 | 2017-10-23
WY | 10 | 2017-09-11 | 2017-12-11 | 2017-12-11 | 2017-11-20
ND | 10 | 2017-09-11 | 2017-12-11 | 2017-12-11 | 2017-11-20
FL | 10 | 2017-09-01 | 2017-12-11 | 2017-12-11 | 2017-11-20
MA | 10 | 2017-09-01 | 2017-12-11 | 2017-12-11 | 2017-11-20
WA | 10 | 2017-09-01 | 2017-12-11 | 2017-12-11 | 2017-11-20
TX | 10 | 2017-09-01 | 2017-12-11 | 2017-12-11 | 2017-11-20
NC | N/A | Not Included | Not included |  | N/A
AK | N/A | Not Included | Not included |  | N/A
CA | N/A | Not Included | Not included |  | N/A
HI | N/A | Not Included | Not included |  | N/A
MT | N/A | Not Included | Not included |  | N/A
SD | N/A | Not Included | Not included |  | N/A
Formulas:
TBYB Filing Date = VLOOKUP([State],'Multi-Tech'!$A2:I52,5,FALSE)
Multi Tech Effective Date = VLOOKUP([State],'Multi-Tech'!$A2:I52,6,FALSE)
Sign Off Date = [Multi Tech Effective Date]-30
Sign Off Date = [TBYB Effective Date]-21

## Change Log
After Updating Change Log, E-Mail Impacted Parties (Systems Teams, Product Owners, CWR)
Date | State | Release | Change | Source
2017-02-16 | MS, VA | 3 | Move MS from R3 to R5, and VA from R3 to R6 | Chad McMann
2017-02-21 | KS | 4 | Move KS from R4 (April) to R6 (June), due to a Rate Revision which we could not combine with. | Chad McMann
2017-03-10 | -- | -- | Added UBI Column to ID SDA states that might be at risk with just the algo filing | David Rogers
2017-03-13 | ID, DE, MA | 4,5,6,7 | Moved ID to R5, DE and MA to R7, due to Omega conflicts (ID and DE) and filing requirements (MA) | Chad McMann
2017-03-16 | TX, NY | 3,4 | TX and NY require additional filing for SDA. We will provide a new filing and launch date as soon as possible. No change to VED in these states. | Chad McMann
2017-03-24 | CT, MD, NV, WV | 6,7,8 | Tentatively adding a release in October and moving these states to the new wave. To be confirmed with Nate and David | Chad McMann
2017-04-18 | RI, MS | 5,6,8 | Moving RI to R8, due to expected filing time, and MS to R6, due to filing requirements. | Chad McMann
2017-05-05 | NM | Tag 2 | Moving NM to replace NJ in PL July release | Zach Fratus